## Task Details
Live Deftsoft Informatics (P) Ltd.
C-139, ELTOP, Ind. Area, Phase 8
Mohali - 160055
Email:business@deftsoft.com
Toll Free(US): +18006702916
Estimated Time Analysis
Website Development - Laravel
Sr No. | Task Name | Working Days | Status
1 | Database Schema Design and creation | 2
2 | Laravel Installation | 2
Laravel (MVC Compliant) Latest Version Installation and Configuration
3 | Admin Panel (Website Back End)
HTML To Admin Template Development
Login Module
| Dashboard:- View Statics for total number of users visited to each page (daily, monthly, yearly) | 2
Manage Profile:- Admin can manage itself profile settings like profile picture, account, password, account settings
| Admin Users Management:- view List of Sub admin users, Add New Sub Admin Users, Allow access level to manage Blog, Manage CMS page, Manage Sub admin users profile. | 3
| CMS Management- View the list of all the front end pages Manage pages (edit/delete) -Add new Sub pages/edit/delete contents Manage SEO Settings | 4
QA/QC Testing and Bug Fixing
| Home Page (Manage header, image banner, and Footer, logo) Services Page (Manage Contents, manage you tube embed video) Clients Page (Manage Contents) About Us (Manage Contents) Our Portfolio (Manage Contents) Web application Development (Manage sub pages and their Contents) Mobile Development (Manage sub pages and their Contents) Digital Marketing (Manage sub pages and their Contents) Others (Manage sub pages and their Contents) Contact Us (Manage Content and Enquiry Form) | 4
Business Partner:- Manage Contents Manage Business enquiry form
| Careers Page:- Manage Categories of job opening and Details Apply Now:- Manage apply now form fields Gallery Button:- Add/edit/delete URL to display the gallery image. | 3
| Basic SEO Management For Each Page- Meta title, Title (H1),Meta keywords Meta description tag for each page, SEO description. Advance SEO Management For Each Page -Rewrites Management (Pattern of Url) -Redirects management (URL's) -SEO-friendly URLs Settings -Image alt tag Updation -One Click Site Map Set Up settings | 3
QA/QC Testing and Bug Fixing
Manage Google Analytics Settings
| Setting Management Email Notification settings, Manage Email Templates | 4
Newsletter Management
| Post/Blogs Management- Add New Blog categories Add New Post/blog, Manage posts (edit, delete) Manage SEO Settings | 2
4 | Front End Modules
HTML To Standard Template Development
| Home Page with Following Sections (SECTIONS SET UP AS PER APPROVED CUSTOM TEMPALTE DESIGN ):- Home Page Section 1 - (Header) Main Navigation (Services, Clients, Portfolio, About Us, Contact Us and Logo (Admin manageable) Home Page Section 2 - Image Banner Home Page Section 3- Our Services tab to display our service images and text with request free consultation button (redirect to contact us form). Home Page Section 4- Our Work images (custom feature to Admin manageable) which redirect users to corresponding associated URL which is set by admin from backend | 3
Home Page Section 5- Testimonial video Section below associated partners logo (random you tube embed video with client name, etc with option to view more will redirect to clients page ) Home Page Section 6- Blog Section with slider and view all blog option will lead to blog page. Home Page Section 7- Contact us form Home Page Section 8-Footer with certification logo, with web application development, mobile development, Digital Marketing, other links option (careers, blog, business partner) section news letter subscribe option, and Social Media icons, copyright text etc
QA/QC Testing and Bug Fixing
| Services Page:- Text based informational page with list of tab for provided services and text slider for clients feedback. | 3
Clients Page:- Informational page with slider to view the list of you tube embed client testimonials videos once select any video it will open a popup to play video. More from clients section has slider to view client project images and text. with text slider for clients feedback.
About us:-Text based informational page with slider for clients feedback.
Our Portfolio:- View portfolio page, they can view portfolio catalogue with view more option will lead to selected portfolio information page. Portfolio information page:- It will simple text based informational page with image slider of project and below text slider for clients feedback.
QA/QC Testing and Bug Fixing
| Web Application Development (Informational section available in footer) -Web/Application Development (Information text based page) -Web Designing (Information text based page) -E-Business Solution (Information text based page) -Enterprise Solution (Information text based page) -Content Management System (Information text based page) | 3
Mobile Development (Informational section available in footer) -iPhone & iPad Applications (Information text based page) - Android & Tab Apps (Information text based page) -Hybrid Applications (Information text based page) -Windows Applications (Information text based page) -Web Applications (Information text based page) -PhoneGap (Information text based page)
Digital Marketing (Informational section available in footer) -Content Creation -Social Media Marketing -Pay per Click -Search Engine Optimization -Online Reputation Management -App Marketing
Others (Informational section available in footer) - Blogs -Careers -Business Partner
| Business Partner:- View text based business partner informational page with an enquiry form | 3
Careers Page:- View text based informational careers page with tabs for view categories wise job opening with apply button and gallery button. Apply Now:- It will lead to a new page to fill the information in the apply now form. Gallery Button:- It will lead third party link to view the gallery images.
QA/QC Testing and Bug Fixing
| Blogs Page- Users can view Blog page Select Blog category Search Blog by keywords View blogs listing Share blog on social media Read all button (open a new page with more details about specific blog) | 4
QA/QC Testing and Bug Fixing
| Newsletter- Users can subscribe Newsletters by submitting their email id | 4
Social Media Sharing: Users can share website contents on social media networks like Facebook, twitter, etc
Contact Us- Users can submit contact us form to website admin
QA/QC Testing and Bug Fixing
5 | Final QA/QC Testing and Bug Fixing
| Development Started Date | 1 Dec, 2016
| Working Days | 49

## Techonology Details
Technology Details
1 | Platform | PHP
2 | Framework | Laravel (MVC Compliant)
3 | Design | HTML/CSS3, Ajax/Js
4 | Database | MySQL